Howard County, Maryland

# (Downtown Columbia TIF Project)

# Special Obligation Bonds

# Financing Timeline

| Date | Event |
| --- | --- |
| Completed | - Distribute Due Diligence Checklist |
| Completed | - Retain Appraiser, Market Analyst, and Engineer |
| Completed | - Submit legislation to County Administrative Officer |
| Completed | - Distribute draft of Market Study |
| 7/8/16 | - Introduction of DTC Legislation |
| 7/11/16; 8:30 am | - County Council Work Session |
| 7/14/16; 6:00 pm | - County Council Public Hearing |
| 7/29/16; 10:00 am | - County Council Legislative Session |
|  | - Signing of Ordinance and Resolution by County Executive |
| 1 Week following passage of legislation |  |
|  | - Distribute draft of Indenture and Funding Agreement |
|  | - Distribute draft of Developer and Development sections of Preliminary Limited Offering Memorandum (PLOM) |
|  | - Distribute draft of TIF Study |
|  | - Provide comments to Market Study draft |
|  | - Distribute draft of Preliminary Limited Offering Memo (PLOM) |
|  | - Complete submission of Due Diligence Checklist items |
|  | - Signing of Ordinance and Resolution by County Executive |
|  | - Distribute comments to TIF Study |
|  | - Distribute draft of Bond Purchase Agreement |
|  | - Distribute draft of Continuing Disclosure Agreements |
|  | - Distribute draft form of legal opinions |
|  | - Circulate 2nd draft of Market Study |
|  | - Distribute draft of Engineer’s Report |
|  | - Distribute draft of Appraisal |
| 2 weeks following passage of legislation |  |
|  | - Provide comments to Appraisal draft |
|  | - Provide comments to 2nd draft of Market Study |
|  | - Provide comments to Engineer’s Report |
|  | - Circulate revised TIF Study |
|  | - Distribute 2nd Draft of TIF Study |
|  | - Distribute 2nd Draft of PLOM, Indenture and Funding Agreement |

| 3 weeks following passage of legislation |  |  |
| --- | --- | --- |
|  |  | - Distribute 3rd Draft of PLOM, Indenture and Funding Agreement |
|  |  | - Distribute 2nd draft of Continuing Disclosure Agreements |
|  |  | - Complete Due Diligence Review |
|  |  | - Distribute 4th Draft of PLOM, Indenture and Funding Agreement |
|  |  | - Finalize Market Study |
|  |  | - Distribute 2nd draft form of legal opinions |
| 4 weeks following passage of legislation |  |  |
|  |  | - Distribute 3rd draft of Continuing Disclosure Agreements |
|  |  | - Distribute draft Closing Checklist |
| 5 weeks following passage of legislation |  |  |
|  |  | - Finalize Engineer’s Report |
|  |  | - Finalize Appraisal |
|  |  | - Finalize Continuing Disclosure Agreements |
|  |  | - Finalize TIF Study |
|  |  | - Finalize BPA, PLOM, Indenture & Funding Agreement |
| 6 weeks following passage of legislation |  |  |
|  |  | - Finalize legal opinions |
|  |  | - Sign-off on Financing Documents |
| 61 days following passage of legislation |  |  |
|  |  | - Effective date of legislation |
|  |  | - Mail PLOM to investors |
|  |  | - Begin marketing Bonds |
| 7 weeks following passage of legislation |  |  |
|  |  | - Investor conference call |
|  |  | - Circulate final closing checklist |
|  |  | - Investor Site Visit (s) |
| 8 weeks following passage of legislation |  |  |
|  | - Pre-pricing call |  |
|  | - Pricing of Bonds |  |
|  | - Sign Bond Purchase Agreement |  |
|  | - Distribute final Limited Offering Memorandum |  |
| 9 weeks following passage of legislation |  |  |
|  | - Circulate draft closing memorandum |  |
|  | - Pre-Closing |  |
|  | - Circulate final closing memorandum |  |
| 10 weeks following passage of legislation |  |  |
|  | - Closing on the 1st series of Bonds |  |